## Backlog Prototype
Row Labels | Sum of hoursAtelier | Sum of hoursElec | Sum of hoursGestion | Sum of hoursLogiciel | Sum of hoursMechanical | Sum of hoursProcede | Sum of hoursRC | Sum of hoursRobot | Sum of monday | Sum of tuesday | Sum of wednesday | Sum of thursday | Sum of friday | Sum of saturday | Sum of sunday | Hours Quoted | Hours Invested
Adaptive Polishing | [15 empty] | 8837 | 0
5187
NFMZ (Naro-Fominsk)
Support remote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5375
AECC Chengdu
One (1) COMBI Robotic Polishing and Profiling System | 431 | 132 | 287 | 16 | 335 | 916 | 102 | 208 | [7 empty] | 2427 | 0
5400
AECC South Industry
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5495
INMAT
TiAl blade polishing study (support Sterna) | 2 | 0 | 0 | 0 | 18 | 328 | 0 | 0 | [7 empty] | 348 | 0
5721
AECC Shenyang
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5722
AECC Guiyang
Compressor blades polishing and profiling cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5724
Skyrizon
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5746
DDF (Da Doug Feng)
Two (2) COMBI Robotic Polishing & Profiling Systems (second order) | 919 | 290 | 434 | 0 | 454 | 985 | 102 | 480 | [7 empty] | 3664 | 0
5753
Wuxi Turbine Blade Co. Ltd.
(3) Compressor Blade Robotic Polishing System | 387 | 161 | 284 | 0 | 328 | 890 | 102 | 246 | [7 empty] | 2398 | 0
5820
Pratt & Whitney (Rzeszow)
Une (1) cellule de polissage adaptatif | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5821
Pietro Rosa T.B.M
Une (1) cellule de polissage adaptatif VSV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5850
Propulsion Technologies International
Ajout mesure de sections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5948
GKN Aerospace (El Cajon)
Adaptive Polishing Study for the F-135 Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
AVI - Blade
1798
Rolls-Royce Derby | [15 empty] | 0 | 0
?tude - Samulet 3 Study P.O. #2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657 | 750.75 | 707 | 728.5 | 659 | 5 | 12 | 20772 | 0
1799
AMRC - Advanced Manufacturing Research Center
Samulet 3 Cell - AMRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
1897
Rolls-Royce Derby
Samulet 2 additional scope 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
1919
Safran Aircraft Engines (Gennevilliers)
Etude Inspection HPT Blade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
1979
Rolls-Royce Derby
Samulet 2 Specularity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
2007
GEA Bromont
Support pattern | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
2014
GEA Bromont
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4454
Pratt & Whitney East Hartford
AVI System Programming | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4681
Rolls-Royce Derby
AVGI for ABCF system #1 | 355 | 276 | 463 | 968 | 409 | 450 | 0 | 211 | [7 empty] | 3132 | 0
4698
Safran Aircraft Engines (Gennevilliers)
Etude AVI Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4699
Avio (Pomigliano)
Ajout Photom?trie - R5 | 7 | 31 | 31 | 19 | 78 | 0 | 60 | 34 | [7 empty] | 260 | 0
4765
Rolls-Royce Derby
Test bench lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4864
Rolls-Royce Derby
Samulet 3 Study P.O. #1 | 0 | 112 | 446 | 1564 | 242 | 1753 | 0 | 45 | [7 empty] | 4162 | 0
4879
Rolls-Royce Derby
?tude - Samulet 3 Study P.O. #3 (2017) | 0 | 36 | 735 | 3752 | 101 | 2153 | 0 | 13 | [7 empty] | 6790 | 0
4894
Rolls-Royce Derby
Amendement - Samulet 3 ? Additional scope for contrast evaluation | 0 | 0 | 40 | 330 | 0 | 0 | 0 | 0 | [7 empty] | 370 | 0
5117
AV&R (D?veloppement Interne)
Optimisation processing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5172
Rolls-Royce Derby
?tude - Samulet 3 Study P.O. #4 (2018 Q1) | 0 | 0 | 639 | 1434 | 466 | 3423 | 0 | 0 | [7 empty] | 5962 | 0
5245
Rolls-Royce Derby
Amendement - Samulet 3 Cell - AMRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5330
Rolls-Royce Derby
?tude - Samulet 3 Study P.O. #4 (2018 Q2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5399
Rolls-Royce Derby
?tude - Samulet 3 Study P.O. #4 (2018 Q3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5462
AV&R (D?mos Client)
Tests PCC inspection | 2 | 0 | 11 | 0 | 33 | 50 | 0 | 0 | [7 empty] | 96 | 0
5510
Rolls-Royce Derby
?tude - Samulet 3 Study P.O. #5 (2018 Q3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5583 | [15 empty] | 31090 | 3319.5832
Pratt & Whitney East Hartford
One (1) Visual Inspection Improvement Retrofit Kit | 61 | 80 | 94 | 52 | 183 | 248 | 16 | 64
5584 | [15 empty] | 0 | 0
Pratt & Whitney East Hartford
Projet d?veloppement inspection PW Hartford (phases 1 ? 3) | 0 | 0 | 158 | 120 | 40 | 1012 | 0 | 0
5634 | [15 empty] | 0 | 0
Pratt & Whitney East Hartford
One (1) Visual Inspection Robotic System + phases 4 to 8 | 286 | 177 | 682 | 1260 | 302 | 2776 | 24 | 172
5635 | [15 empty] | 0 | 0
Rolls-Royce Derby
Samulet 3 2019 - R2 | 0 | 0 | 253 | 796 | 0 | 1044 | 0 | 0
5636 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Demo Client PW US | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5659 | [15 empty] | 0 | 0
Rolls-Royce Derby
OGV inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5660 | [15 empty] | 0 | 0
Rolls-Royce Derby
Compressor blade inspection study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5875 | [15 empty] | 0 | 0
Rolls-Royce Derby
One (1) Visual Inspection Robotic System (TBF blade) | 320 | 199 | 265 | 210 | 378 | 512 | 126 | 224
5876 | [15 empty] | 0 | 0
Rolls-Royce Derby
TBF Visual inspection Study (MCRL5) | 12 | 0 | 196 | 120 | 68 | 1260 | 0 | 0
5914 | [15 empty] | 0 | 0
Rolls-Royce Derby
Rolls-Royce - AVI Study Trent 1000 recipe + MES | 3 | 0 | 197 | 676 | 42 | 744 | 0 | 0
5970 | [15 empty] | 0 | 0
Lisi (Rzeszow)
Une (1) cellule d;Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L657 DC1 | [15 empty] | 0 | 0
Avio (Pomigliano)
Amendement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controlled Polishing | [15 empty] | 0 | 0
1999
Safran Aircraft Engines (Gennevilliers)
Polissage Distributeur HP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4671
Pratt & Whitney (PCI) - Columbus
One (1) Robotic Airfoil Polishing and Profiling System R3 | 422 | 450 | 639 | 45 | 752 | 1543 | 1483 | 604 | 166 | 189 | 198 | 211.0833 | 180.5 | 16.25 | 24 | 5938 | 984.8333
4789
Pratt & Whitney (PCI) - Columbus
Six (6) Robotic Polishing & Profiling Systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4938
BTL (Blades Technology Ltd)
Polishing Study - Phase 2 - R2 | 0 | 0 | 32 | 0 | 0 | 226 | 0 | 10 | [7 empty] | 268 | 0
4952
Anhui Yingliu Group
Two (2) Turbine blade polishing and TE profiling systems R7 | 446 | 381 | 650 | 72 | 633 | 2477 | 0 | 750 | 238.25 | 219.75 | 200.5833 | 204.5833 | 252.5833 | 48.5 | 32.75 | 5409 | 1196.9999
4984
PCC Airfoils SMP Wickliffe
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4996
Safran Helicopter Engines (Bordes)
?tude - Polissage Aubes HVOF - R5 | 0 | 0 | 165 | 0 | 96 | 856 | 0 | 16 | 147.75 | 152.5 | 145 | 178 | 117.75 | 1 | 5 | 1133 | 747
5065
DRT Power Systems LLC
One (1) LPC Vane Robotic Polishing & Deburring System | 371 | 254 | 420 | 40 | 532 | 1468 | 0 | 452 | [7 empty] | 3537 | 0
5072
Safran Helicopter Engines (Bordes)
Une (1) Cellule Polissage aubes HVOF + Cuivre - R2 | 436 | 229 | 531 | 22 | 510 | 856 | 0 | 368 | [7 empty] | 2952 | 0
5084
New England Airfoil Products
One (1) Compressor Blade Robotic Polishing and Profiling Systems (Military) | 606 | 662 | 354 | 45 | 963 | 779 | 18 | 485 | [7 empty] | 3912 | 0
5268
Rolls-Royce Derby
Turbine Blade Robotic Polishing Study R2 | 30 | 0 | 128 | 0 | 85 | 956 | 0 | 22 | 10 | 12.5 | 8.5 | 4.5 | 6.5 | 1.5 | 0 | 1221 | 43.5
5317
Lisi (Rzeszow)
D?veloppement proc?d? controlled polishing | 0 | 0 | 30 | 0 | 18 | 234 | 0 | 0 | 33.5 | 49.75 | 71.25 | 54.5 | 41.75 | 0 | 0 | 282 | 250.75
5344
Rolls-Royce High Temperature Composites
composite plate adaptive polishing test | 0 | 0 | 25 | 0 | 20 | 137 | 0 | 11 | 16.25 | 17.25 | 16 | 15.75 | 31.25 | 0 | 0 | 193 | 96.5
5360
BTL (Blades Technology Ltd)
One (1) Robotic Polishing & Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5386
Pratt & Whitney (PCI) - Columbus
Garantie et Support - One (1) Robotic Airfoil Profiling & Polishing System R3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5455
Wuxi Turbine Blade Co. Ltd.
One (1) COMBI Robotic Polishing and Profiling System | 387 | 161 | 284 | 0 | 328 | 890 | 102 | 246 | [7 empty] | 2398 | 0
5496
Safran Aircraft Engines (Ch?tellerault)
Une (1) cellule de polissage soudure sur secteur DHP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5497
Safran Aircraft Engines (Ch?tellerault)
Une (1) cellule de polissage de MHP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5503
Safran Aircraft Engines Mexico (Quer?taro)
Etude - Polissage composite aube fan Leap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5531
AECC South Industry
Small blade Profiling & Polishing Study | 8 | 0 | 111 | 0 | 72 | 748 | 0 | 0 | [7 empty] | 939 | 0
5541
GKN Aerospace (Manchester)
Polishing cell for Fan Blade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5628
Sterna Aviation Technology & Service Co. Ltd.
Cellule demo combo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5631
PWMS
OEM fan blade polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5666
Lisi (Rzeszow)
Two (2) COMBI Robotic Polishing and Profiling Systems - R6 | 678 | 233 | 511 | 0 | 312 | 724 | 128 | 322 | [7 empty] | 2908 | 0
5680 | [15 empty] | 49846 | 3086.4168
Pratt & Whitney (PCI) - Columbus
One (1) Robotic Compressor Blade Polishing and Profiling System (2e Unit) | 399 | 180 | 307 | 8 | 459 | 864 | 127 | 242
5720 | [15 empty] | 0 | 0
AECC BIAM
HPT blade blending + polishing and TTE cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5749 | [15 empty] | 0 | 0
INMAT
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5750 | [15 empty] | 0 | 0
AECC BIAM
HPT blade blending polishing and TTE study (support a Sterna) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5772 | [15 empty] | 0 | 0
Hanwha Aerospace Co. LTD
One (1) Mid-Sized Robotic Polishing and Profiling System | 858 | 279 | 525 | 0 | 953 | 812 | 114 | 795
5774 | [15 empty] | 0 | 0
Rolls-Royce High Temperature Composites
CMC seals segments Polishing Study Phase 2 | 4 | 0 | 34 | 0 | 8 | 130 | 0 | 16
5797 | [15 empty] | 0 | 0
Arconic (Dives)
Une (1) cellule de polissage LPT Leap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5808 | [15 empty] | 0 | 0
Hanwha Aerospace Co. LTD
Teach of one (1) new part + Advanced Training R2 | 5 | 0 | 45 | 0 | 42 | 778 | 0 | 0
5854 | [15 empty] | 0 | 0
AV&R (D?mos Client)
LPT Polishing Trials pour PCC | 3 | 0 | 22 | 0 | 33 | 130 | 0 | 0 | 40 | 56.75 | 34.8333 | 49.25 | 45 | 0 | 0
5882 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
COMBI Systems Second Drawer Robotic Simulations | 0 | 0 | 6 | 0 | 5 | 33 | 0 | 29
5921 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Travail de Layout sur Grosse Cellule Polissage & Profilage | 52 | 72 | 109 | 0 | 386 | 20 | 0 | 230
5968 | [15 empty] | 0 | 0
GKN Aerospace (El Cajon)
Weight reduction polishing study on Engine case | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5992 | [15 empty] | 0 | 0
Turbocoating (Tarbes)
?tude Polissage HVOF sur HPT RTM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cosmetic Polishing | [15 empty] | 0 | 0
4689
GKN Aerospace (Orangeburg)
Robotic polishing cell Phase 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4857
GKN Aerospace (Orangeburg)
Lipskin Robotic Grinding and Pre-polishing prototype Cell 1last payment | 0 | 1553 | 1064 | 726 | 2214 | 554 | 822 | 1222 | 0.5 | 0.5 | 0.75 | 0.5 | 2.5 | 0 | 0 | 8155 | 4.75
4876
GEE Greenville (MRO)
One (1) Nozzle Polishing System MRO (L645) | 308 | 465 | 545 | 9 | 504 | 951 | 0 | 941 | 0.5 | 1 | 0 | 0.5 | 0 | 0 | 0 | 3723 | 2
5039
GKN Aerospace (Orangeburg)
Lipskin Robotic Grinding and Pre-polishing Cell (Phase 2) (Line Item 1) R5 | 0 | 1553 | 1064 | 726 | 2214 | 554 | 822 | 1222 | [7 empty] | 8155 | 0
5097
GKN Aerospace (North Charlestown)
Two (2) Mid-Sized Robotic Polishing and Profiling Systems R2 | 1127 | 309 | 952 | 0 | 1126 | 1498 | 200 | 956 | 95 | 126 | 145 | 101.25 | 67 | 0 | 0 | 6168 | 534.25
5138
GEE Greenville (MRO)
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5217
GEE Greenville (MRO)
Amendement - One (1) Nozzle Polishing System MRO (L645) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5257
GEE - Singapore
Spare Parts Right angle tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5287
GEE - Singapore
Spare Parts- Used HF Motor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5308
AECC Chengdu
One (1) Fan Blade Robotic Polishing and Profiling System | 511 | 575 | 762 | 88 | 975 | 700 | 0 | 523 | [7 empty] | 4134 | 0
5310
GEE Greenville (MRO)
Amendement - One (1) Nozzle Polishing System MRO (L645) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5355
TECT Power (Utica)
Two (2) Robotic Fan Blade Leading Edge Polishing Systems R3 | 374 | 355 | 344 | 32 | 585 | 584 | 102 | 438 | 548.8 | 477.0334 | 467.6667 | 542.1001 | 481.0666 | 1 | 17 | 2814 | 2534.6668
5356
Techjet Airfoils Ltd
One Polishing Cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5376
DDF (Da Doug Feng)
One (1) COMBI Robotic Polishing and Profiling System | 919 | 290 | 434 | 0 | 454 | 985 | 102 | 480 | [7 empty] | 3664 | 0
5419
GKN Aerospace (Orangeburg)
Amendement - Dismantling and Installation Prototype Cell at Orangeburg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5420
GKN Aerospace (Orangeburg)
Onsite assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5444
ITOCHU Machine Tools
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5445
ITOCHU Machine Tools
Polishing and profiling study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5452
Hanwha Aerospace Co. LTD
One (1) COMBI Robotic Polishing and Profiling System - R5 | 348 | 157 | 237 | 0 | 293 | 628 | 79 | 275 | 1 | 1 | 4 | 2.25 | 0.5 | 0 | 0 | 2017 | 8.75
5460
Arconic Dover
Segment Polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5482
TECT Power (Utica)
Garantie et support : Two (2) Robotic Fan Blade Leading Edge Polishing Systems R3 | 374 | 355 | 344 | 32 | 585 | 584 | 102 | 438 | [7 empty] | 2814 | 0
5501
Lisi (Parthenay)
Une (1) cellule de finition VSV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5508
Safran Aircraft Engines (Gennevilliers)
Industrialisation MHTTP400 et formation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
5513
Lisi (Marmande)
Banque support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
5517
McStarlite Company
One (1) Lipskin Segments Robotic Polishing System | 394 | 340 | 332 | 5 | 417 | 794 | 63 | 446 | [7 empty] | 2791 | 0
5527
Ivchenko-Progress
One (1) COMBI Robotic Polishing and Profiling System - R2 | 396 | 219 | 497 | 0 | 222 | 1022 | 260 | 224 | [7 empty] | 2840 | 0
5544
TECT Power (Utica)
Advance training on Brainwave | 0 | 0 | 25 | 0 | 0 | 0 | 212 | 0 | [7 empty] | 237 | 0
5558
Lutsk Repair Plant Motor
One (1) COMBI Robotic Polishing and Profiling System | 395 | 200 | 277 | 0 | 269 | 852 | 113 | 228 | [7 empty] | 2334 | 0
5559 | [15 empty] | 0 | 0
TECT Power (Utica)
Amendement - Two (2) Robotic Fan Blade Leading Edge Polishing Systems R3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5594 | [15 empty] | 0 | 0
Rolls-Royce Derby
One (1) Compressor blade Polishing System (Iain W.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5633 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
Adaptive machining | 0 | 4 | 0 | 0 | 44 | 0 | 200 | 40
5652 | [15 empty] | 0 | 0
GKN Aerospace (Orangeburg)
Amendement - Dismantling and Installation Prototype Cell at Orangeburg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5656 | [15 empty] | 0 | 0
Rolls-Royce plc
Compressor blade Polishing Study Phase 2 (Iain W.) Rolls-Royce Derby | 0 | 0 | 30 | 0 | 8 | 200 | 0 | 0
5668 | [15 empty] | 0 | 0
Lisi (Marmande)
?tude - Polissage BA GE9X | 16 | 0 | 28 | 0 | 4 | 188 | 0 | 4 | 64.25 | 66.25 | 88.75 | 67.75 | 51.75 | 10.5 | 0
5669 | [15 empty] | 0 | 0
Lisi (Marmande)
Une (1) cellule de polissage BA GE9X R4 | 250 | 239 | 347 | 0 | 400 | 380 | 80 | 292
5699 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
SP 1re partie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5700 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
SP 2eme partie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5751 | [15 empty] | 0 | 0
AECC Guiyang
Compressor blades polishing and profiling Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5763 | [15 empty] | 0 | 0
Advanced Ceramic Coatings
Fuel Nozzle Coating Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5768 | [15 empty] | 0 | 0
Mecafi (Ch?tellerault)
Deux (2) cellules de polissage et ?bavurage OGV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5775 | [15 empty] | 0 | 0
PCC - Crooksville
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5776 | [15 empty] | 0 | 0
Arconic Wichita Falls
Multi-Segments Vanes Polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5779 | [15 empty] | 0 | 0
Moeller Aerospace Technologies
Ti LPT Blade Polishing/Deburring | 804 | 260 | 496 | 4 | 897 | 858 | 160 | 674
5833 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Tests de Polissage & Profilage pour N.E.A.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 14.5 | 19.0833 | 28.75 | 22 | 0 | 0
5840 | [15 empty] | 0 | 0
Broad Peak Manufacturing
One (1) Knee Implants polishing system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5857 | [15 empty] | 0 | 0
Natesan Synchrocones Pvt. Ltd.
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5859 | [15 empty] | 0 | 0
Azad Engineering Pvt. Ltd
Four (4) COMBI Robotic Polishing and Profiling Systems - R1 | 1223 | 367 | 799 | 8 | 420 | 1084 | 169 | 565
5866 | [15 empty] | 0 | 0
Leistritz Turbinenkomponenten Remscheid GmbH
M.L.E. Finishing Pre-Engineering Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5885 | [15 empty] | 0 | 0
Flame Spray North America
TBC Nozzle Polishing | 429 | 206 | 428 | 8 | 353 | 304 | 410 | 302
5900 | [15 empty] | 0 | 0
Guizhou Hangfei Precision Manufacturing Co. Ltd. | [15 empty] | 0 | 0
One (1) COMBI Robotic Polishing and Profiling System | 396 | 217 | 245 | 0 | 254 | 562 | 190 | 206
5917
Broad Peak Manufacturing | [15 empty] | 0 | 0
Essais de polissage sur genoux | 9 | 0 | 73 | 0 | 63 | 256 | 0 | 16
5922
Ultratech | [15 empty] | 0 | 0
One (1) COMBI Robotic Polishing and Profiling System | 387 | 192 | 371 | 0 | 211 | 562 | 190 | 211
5924
Corrtech Energy Limited | [15 empty] | 0 | 0
One (1) COMBI Robotic Polishing and Profiling System | 355 | 166 | 243 | 8 | 286 | 582 | 157 | 290
5929
TECT Power (Utica) | [15 empty] | 0 | 0
support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5955
Proxmus (Elbl?g) | [15 empty] | 0 | 0
Une (1) cellule de polissage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5962
TECT Power (Utica) | [15 empty] | 0 | 0
One (1) Robotic Fan Blade Leading Edge Polishing | 320 | 103 | 136 | 0 | 137 | 216 | 126 | 138
5971
XRA (Xi?an XR Aero-Components Co.; Ltd) | [15 empty] | 0 | 0
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5972
Rolls-Royce plc | [15 empty] | 0 | 0
Trent 1000 Rotor 1 and Rotor 2 polishing demonstration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 199 | 0
5986
Superalloy Manufacturing Solutions Corporation
Study - Polishing Process Assessment for Forged Vanes | 3 | 0 | 24 | 0 | 34 | 138 | 0 | 0 | [7 empty] | 199 | 0
5989
Mitsubishi Hitachi Power Systems Americas
IGT Compressor Blade Airfoils Blending/Polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5999
AV&R (D?mos Client)
D?mo polishing Hangfei Ghuizou | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
Deburring
131
Wolseley Industrial Group | [15 empty] | 0 | 0
Spare parts L1219-4316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1739
Turbine Jet | [15 empty] | 0 | 0
Support contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1893
GEA Piedmont | [15 empty] | 0 | 0
Support contract 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1918
GEA Piedmont | [15 empty] | 0 | 0
Services Design & Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1978
GEA Piedmont | [15 empty] | 0 | 0
Emergency visit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4569
Wolseley Industrial Group | [15 empty] | 0 | 0
Spare parts L1219-2120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4584
GEA Piedmont | [15 empty] | 0 | 0
C-131 DC-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4628
Turbine Jet | [15 empty] | 0 | 0
support 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4811
GEA Piedmont | [15 empty] | 0 | 0
Two (2) Robotic Deburring Cells R1 | 390 | 381 | 226 | 24 | 606 | 28 | 0 | 640
4831
GEA Piedmont | [15 empty] | 0 | 0
remote support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4832
GEA Piedmont | [15 empty] | 0 | 0
onsite support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4871
GEA Piedmont | [15 empty] | 0 | 0
Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4904
Excent | [15 empty] | 0 | 0
Support Robot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
4912
GEA Piedmont | [15 empty] | 0 | 0
Process + Gripper | 0 | 0 | 57 | 0 | 0 | 376 | 0 | 102
4962
Safran Aircraft Engines (Gennevilliers) | [15 empty] | 0 | 0
?tude - Ajustage d;aubes Militaires | 3 | 0 | 55 | 0 | 23 | 386 | 0 | 0
5019
Turbine Jet | [15 empty] | 0 | 0
Tooling Retrofit on L-599 Hard Face Cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 30.5 | 32.75 | 32 | 33.5 | 0 | 2
5056
GEA Piedmont | [15 empty] | 0 | 0
Amandement - DC-01 - Two (2) Robotic Deburring Cells R1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5177
Superalloy Manufacturing Solutions Corporation master | [15 empty] | 0 | 0
Blisks deburring/polishing F-135 (Military) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5320
Turbine Jet | [15 empty] | 0 | 0
Two (2) Blade Deburring Cells R3 | 375 | 257 | 219 | 18 | 311 | 45 | 76 | 544
5367
Turbine Jet | [15 empty] | 0 | 0
Assatec Retrofit | 0 | 0 | 0 | 60 | 0 | 0 | 100 | 0
5404
GEA Piedmont | [15 empty] | 0 | 0
3 days onsite training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5421
AV&R (D?mos Client) | [15 empty] | 0 | 0
Essais d;?bavurage sur Aubes pour Turbine Jet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5754
ITP | [15 empty] | 0 | 0
Une (1) cellule d;?bavurage de LPT multivane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5762
Avio (Bielsko) | [15 empty] | 0 | 0
LEAP LPT multivane deburring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5766
Safran Aircraft Engines (S?dzisz?w) | [15 empty] | 0 | 0
Une (1) et trois (3) cellule(s) d;?bavurage de LPT blade LEAP | 290 | 197 | 226 | 0 | 491 | 137 | 63 | 510
5767
Chromalloy (Rochefort) Malichaud Atlantique | [15 empty] | 0 | 0
Une (1) ou trois (3) cellule(s) d;?bavurage de LPT blade LEAP | 290 | 197 | 226 | 0 | 491 | 137 | 63 | 510
5769
MTU Aero Engines (Jasionka) | [15 empty] | 0 | 0
Une (1) cellule d;?bavurage de LPT blade GTF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5781
Pratt & Whitney Canada Halifax | [15 empty] | 0 | 0
Blade Deburring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5822
Safran Helicopter Engines (Bordes) | [15 empty] | 0 | 0
?tude - ?bavurage Aubes HVOF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5870
Pratt & Whitney (PCI) - Columbus | [15 empty] | 0 | 0
Services part integration deburring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5886
ELIMETAL INC. | [15 empty] | 0 | 0
De-Burring parts.- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1786 | 0
5893
Pratt & Whitney (PCI) - Columbus
One (1) Robotic Deburring System | 290 | 197 | 211 | 0 | 418 | 257 | 63 | 350 | [7 empty] | 1786 | 0
5918
Abrasive-Form
Deburring Cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5953
GKN Aerospace (Bristols)
Deburring and Polishing Prysmatic Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5963
Pratt & Whitney AutoAir - Lansing
Brushing Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5974
GEA Piedmont
Deburr cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5975
GEA Piedmont
Deburr cell for airfoil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
81
Wolseley Industrial Group
Spare parts L1219-2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
Die Cast - LEGACY
1975
Thomas & Betts | [15 empty] | 0 | 0
Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4444
Canimex | [15 empty] | 0 | 0
Impartition for technology transfer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5991
Canimex | [15 empty] | 0 | 0
Entente Robot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Die Cast - Production
2456 | [15 empty] | 0 | 0
Thomas & Betts
Die Cast Pieces | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-metalic Robotic Operation | [15 empty] | 0 | 0
114
GEA CAR
Training Ellisville | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4653
BAIN MAGIQUE
Amendement-Robot aux Accessoires | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4696
BAIN MAGIQUE
Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
Pin Blending
4998
Rolls-Royce Derby | [15 empty] | 0 | 0
HPT pins removal and polishing Study | 18 | 0 | 325 | 0 | 164 | 1348 | 0 | 0 | 359.3333 | 376.1666 | 364.5 | 436.5833 | 327.0834 | 7 | 2.5
5034
Rolls-Royce ABCF Rotherham | [15 empty] | 0 | 0
Machine Rental - ABCF IP+HP Turbine blade Pins Removal and polishing cell (first cell) | 111 | 48 | 189 | 52 | 439 | 518 | 120 | 132 | 85.25 | 105.25 | 109.5 | 106.5 | 112 | 0 | 0
5165
CHROMALLOY (Palm Beach) | [15 empty] | 0 | 0
Process Assessment - Turbine Blades Pin Removal / Polishing | 0 | 22 | 44 | 0 | 56 | 286 | 0 | 0
5244
Safran Aircraft Engines (Gennevilliers) | [15 empty] | 0 | 0
Spare Parts 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5350
Safran Aircraft Engines (Gennevilliers) | [15 empty] | 0 | 0
Spare parts 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5414
Rolls-Royce ABCF Rotherham | [15 empty] | 0 | 0
ABCF IP+HP Turbine blade pins removal and polishing cell order #2 (14 systems) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5818
CPP Europe (Rzesz?w) | [15 empty] | 0 | 0
Une (1) cellule de pin blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5819
Di Matteo | [15 empty] | 0 | 0
Une (1) cellule de pin blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Polishing Non-Attribu?
00127 | [15 empty] | 0 | 0
GEE - Singapore
Spare parts 1000064742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | [15 empty] | 0 | 0
GEE - Singapore
Spare parts 740012523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1816 | [15 empty] | 0 | 0
UTAS Aerostructures - Chula Vista
Lipskins System Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1861b | [15 empty] | 0 | 0
GEE Greenville (MRO)
Nozzle Polishing Development System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1905 | [15 empty] | 0 | 0
GEE Greenville (NM)
Support 2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1990 | [15 empty] | 0 | 0
Lisi (Marmande)
Composite Fan Blade LE Polish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | [15 empty] | 0 | 0
GEE Greenville (NM)
Amendement - M10 Nozzle Polishing System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4527 | [15 empty] | 0 | 0
BTL (Blades Technology Ltd)
Feasibility Study ? Airfoil polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4611 | [15 empty] | 0 | 0
UTAS Aerostructures - Chula Vista
remote support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4634 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
HPT Polishing & Blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4662 | [15 empty] | 0 | 0
GEE - Singapore
DC-09 Terry tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4710 | [15 empty] | 0 | 0
GEA Bromont
UltraPolish cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4741 | [15 empty] | 0 | 0
UTAS Aerostructures - Chula Vista
remote support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4766 | [15 empty] | 0 | 0
Lisi (Marmande)
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4806 | [15 empty] | 0 | 0
GKN Aerospace (Orangeburg)
Amendement - DC-01 Lipskin Polishing | 0 | 546 | 338 | 525 | 1249 | 52 | 85 | 359
4815 | [15 empty] | 0 | 0
Lisi (Marmande)
Ajout Orbitale Lisi Marmande R2 | 0 | 0 | 20 | 0 | 0 | 136 | 0 | 0
4841 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Polishing M3 TEST PERFO BANDE ABRASIVES (FIXE) | 0 | 18 | 132 | 18 | 157 | 595 | 0 | 90
4847 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Polishing M43 STRATEGIE DE FEEDBACK PH4 (tests perfo LVDT) (0.91) | 0 | 73 | 242 | 43 | 200 | 1423 | 0 | 275 | 325 | 369.75 | 347.55 | 348 | 363.75 | 0 | 0
4848 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Polishing M6 G?N?RATION RECETTES (AJUST PARAM) PH0; d?finition du besoin et des phases (1.12) | 0 | 0 | 10 | 0 | 0 | 67 | 0 | 0
4849 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Polishing M26 GENERATION RECETTES PH2; TBD apr?s PH0 (1.17) | 0 | 0 | 64 | 325 | 0 | 101 | 0 | 0
4850 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
(1.20) Polishing M16 outiilage sur compliance | 0 | 265 | 261 | 11 | 537 | 714 | 204 | 443
4851 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Polishing M5 STRAT?GIE CTL (ADAPTATIF) (1.25) | 0 | 18 | 103 | 0 | 166 | 414 | 0 | 90
4854 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Outils logiciel d;aide au teach de polishing | 0 | 0 | 89 | 529 | 0 | 211 | 0 | 0
4855 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Budget FRAR discretionaire 2016 pour urgence ou opportunisme | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0
4865 | [15 empty] | 0 | 0
GEA Bromont
Amendement - UltraPolish cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4990 | [15 empty] | 0 | 0
GEA Bromont
Amendement - UltraPolish cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4991 | [15 empty] | 0 | 0
GEA Bromont
Amendement - UltraPolish cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5018 | [15 empty] | 0 | 0
GEE - Singapore
Spare parts - Terry tools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5063 | [15 empty] | 0 | 0
UTAS Aerostructures - Chula Vista
Service Onsite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5109 | [15 empty] | 0 | 0
Lisi (Marmande)
remote support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5133 | [15 empty] | 0 | 0
GKN Aerospace (Orangeburg)
On-site support Demo Cell at GKN Orangeburg | 0 | 0 | 23 | 0 | 0 | 330 | 0 | 132
5134 | [15 empty] | 0 | 0
GKN Aerospace (Orangeburg)
Dismantling and Installation Prototype Cell at Orangeburg | 0 | 170 | 101 | 0 | 506 | 0 | 0 | 0
5146 | [15 empty] | 0 | 0
Lisi (Marmande)
Support urgent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5185 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Essais de blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5211 | [15 empty] | 0 | 0
GEE Greenville (NM)
System Dual Airfoil Nozzle Polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5218 | [15 empty] | 0 | 0
GEE Greenville (MRO)
Amendement - One (1) Nozzle Polishing System MRO (L645) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5250 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Tests D?mo sur Pi?ces de AECC | 0 | 0 | 27 | 0 | 29 | 181 | 0 | 0
5292 | [15 empty] | 0 | 0
PG Technologies
Onsite visit visit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5309 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Tests Lisi Polissage 2 ref | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5466 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
Spare parts 1ere urgence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5477 | [15 empty] | 0 | 0
AV&R (D?veloppement Interne)
Fabrication de trois (3) Syst?mes Polissage & Profilage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5488 | [15 empty] | 0 | 0
Sterna Aviation Technology & Service Co. Ltd.
Formation 3 mois | 0 | 3 | 23 | 1 | 3 | 191 | 142 | 78 | 3 | 7 | 0.5 | 0.5 | 0.5 | 0 | 0
5533 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Tests Polissage pour GKN Newington | 2 | 0 | 26 | 0 | 26 | 168 | 0 | 0
5591 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Tests de Polissage pour TechJet | 2 | 0 | 35 | 0 | 33 | 224 | 0 | 0
5593 | [15 empty] | 0 | 0
AV&R (D?mos Client)
Compressor blade Polishing Study (Iain W.) Rolls-Royce Derby | 0 | 0 | 20 | 0 | 8 | 120 | 0 | 0 | 10.5 | 18 | 10.25 | 9.25 | 9 | 0 | 0
5611 | [15 empty] | 0 | 0
GEE Greenville (MRO)
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5637 | [15 empty] | 0 | 0
Lisi (Marmande)
SP P422432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5867 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
formation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Profiling | [15 empty] | 0 | 0
00057
GE Energy others
DC-02 Hole clearing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
00108 | [15 empty] | 0 | 0
GEA CAR
DC-06 Positionnement custom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
00152 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
PCI - Diamond roller | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1693 | [15 empty] | 0 | 0
BTL (Blades Technology Ltd)
Retrofit Double Head | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1809-1 | [15 empty] | 0 | 0
GEA Rutland
Support contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1845 | [15 empty] | 0 | 0
GEA Bromont
LE Profiling (6x double cells) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1854 | [15 empty] | 0 | 0
GEA CAR
TE Profiling x 2 (HPT et ATI) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1864 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
One (1) Fan blade BA Profiling System - R2 | 472 | 148 | 320 | 224 | 653 | 471 | 0 | 321
1881 | [15 empty] | 0 | 0
Safran Aircraft Engines (Gennevilliers)
Etude Reprise Bord Fuite (Multiple LPT Profiling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1884 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
onsite support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1890 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
Teach & Tooling Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1891 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
Profiling Cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
1902 | [15 empty] | 0 | 0
GEA CAR
Teach GEA CAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.5 | 215.25 | 233.9167 | 231.75 | 235.8333 | 1 | 0
1907 | [15 empty] | 0 | 0
Hyatech
Profiling Cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1913 | [15 empty] | 0 | 0
GEA CAR
Pimp Profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1915 | [15 empty] | 0 | 0
Pietro Rosa T.B.M
LE Profiling cell Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1932 | [15 empty] | 0 | 0
Lisi (Bologne)
On-site Visit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1934 | [15 empty] | 0 | 0
Turbine Jet
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1935 | [15 empty] | 0 | 0
Lisi (Marmande)
GE9x part teach | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1938 | [15 empty] | 0 | 0
Lisi (Bologne)
Remise ? niveau | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1941 | [15 empty] | 0 | 0
Airfoil Services Sdn. Bhd. (ASSB)
HPC Recontouring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1947 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
PC-Share upgrade and support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1949 | [15 empty] | 0 | 0
GEA Bromont
Onsite visit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1952 | [15 empty] | 0 | 0
Pratt & Whitney (PCI) - Columbus
Additional services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1968 | [15 empty] | 0 | 0
Prodoc Lt?e | [15 empty] | 0 | 0
Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1969
GEA Rutland | [15 empty] | 0 | 0
spare parts shafts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1976
GEA Rutland | [15 empty] | 0 | 0
Keyence spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1981
Safran Aircraft Engines (Gennevilliers) | [15 empty] | 0 | 0
Etude Profiling BA Titane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8005 | 218
1988
Lisi (Marmande)
One (1) GE9x Blades Robotic Profiling System R7 | 280 | 324 | 408 | 158 | 478 | 744 | 0 | 216 | 39.25 | 46.5 | 51.25 | 37 | 27.5 | 12 | 4 | 2608 | 217.5
2013
GEA Bromont
Services - Impartition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4508
Pratt & Whitney (PCI) - Columbus
Three (3) Leading/Trailing Edge Robotic Profiling Cells R3 | 652 | 468 | 314 | 361 | 1083 | 453 | 81 | 298 | [7 empty] | 3710 | 0
4511
BTL (Blades Technology Ltd)
Two (2) Profiling Cells | 0 | 292 | 220 | 179 | 627 | 205 | 0 | 164 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1687 | 0.5
4523
Airfoil Services Sdn. Bhd. (ASSB)
HPC Recontouring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4545
GEA Bromont
Profiling - Repeat L700 Double | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4561
Airfoil Services Sdn. Bhd. (ASSB)
Amendement - HPC Recontouring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4585
BTL (Blades Technology Ltd)
F Class+ profiling development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4660
GEA Hooksett
support 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4664
Wolseley Industrial Group
dc05 - Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4670 | [15 empty] | 0 | 0
Rolls-Royce Derby
Turbines Thin Trailing Edge Feasability Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4673 | [15 empty] | 0 | 0
BTL (Blades Technology Ltd)
Base section profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4690 | [15 empty] | 0 | 0
GEA Hooksett
J85 STG 1-2-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4691 | [15 empty] | 0 | 0
GEA Hooksett
J85 STG 5-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4692 | [15 empty] | 0 | 0
GEA Hooksett
J85 STG 4-7-8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4705 | [15 empty] | 0 | 0
Hyatech | [15 empty] | 0 | 0
Two (2) LE and TE Robotic Profiling Systems - R4 | 503 | 182 | 258 | 2 | 229 | 365 | 517 | 206 | 61.75 | 59.5 | 90.25 | 104.25 | 88.5 | 0 | 0
4726
GEA Hooksett | [15 empty] | 0 | 0
J85 STG 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4742
Rolls-Royce Derby | [15 empty] | 0 | 0
?tude - Turbines Thin Trailing Edge Feasability Study Phase 2 | 0 | 9 | 285 | 274 | 87 | 1465 | 0 | 63 | [7 empty] | 11347 | 113.75
4744
GEE - Singapore
spare parts Grab Latch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4770
BTL (Blades Technology Ltd)
LER-TER Profile Acquisition Functionalities Retrofit Kit R2 | 0 | 155 | 96 | 63 | 175 | 315 | 0 | 94 | [7 empty] | 898 | 0
4771
Safran Aircraft Engines (Gennevilliers)
Etude Reprise Bord Fuite (Multiple LPT Profiling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4774
Airfoil Services Sdn. Bhd. (ASSB)
Extra days from Max Marcotte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4798
GEA Bromont
Two (2) LE Profiling 3rd Generation (CL Version) R3 | 821 | 522 | 240 | 54 | 982 | 0 | 0 | 845 | [7 empty] | 3464 | 0
4810
Lisi (Marmande)
Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4838
AV&R (D?veloppement Interne)
Profiling M8 Outils de correlation PH 0 (0.90) | 0 | 0 | 16 | 24 | 0 | 60 | 0 | 0 | [7 empty] | 100 | 0
4852
AV&R (D?veloppement Interne)
Profiling M1 Quantification des performances profiling (1.10) | 0 | 0 | 78 | 48 | 0 | 360 | 0 | 0 | [7 empty] | 486 | 0
4853
AV&R (D?veloppement Interne)
Profiling M11 Formule d;enl?vement de mati?re; vitesse vs aire enlev?e; la formule n;est pas coh?rente (1.14) | 0 | 0 | 66 | 0 | 36 | 314 | 0 | 0 | [7 empty] | 416 | 0
4856
AV&R (D?veloppement Interne)
Deburring M17 Compliance hard tools tests | 0 | 0 | 34 | 0 | 0 | 250 | 0 | 0 | [7 empty] | 284 | 0
4873
Lisi (Bologne)
Service-formation | 0 | 0 | 16 | 0 | 0 | 136 | 0 | 0 | [7 empty] | 152 | 0
4889
GEA Bromont
remote support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4933
GEA Rutland
Three (3) Class B -E Profiling cells | 842 | 132 | 477 | 92 | 314 | 178 | 0 | 484 | [7 empty] | 2519 | 0
4937
Lisi (Marmande)
Visite onsite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
4971
GEA Bromont
Services impartition senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5004
AV&R (D?veloppement Interne)
Augmentation de la Robustesse;Qualit? et Rapidit? de la Calibration des Keyences | 0 | 0 | 54 | 246 | 0 | 0 | 0 | 203 | [7 empty] | 503 | 0
5014
Lisi (Bologne)
Spare parts diamond | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 9.25 | 8.5 | 10.5 | 8.25 | 0 | 0 | 0 | 49
5094
BTL (Blades Technology Ltd)
Support From F-04585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5113
Lisi (Marmande)
Modifications cellule profiling de Bologne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5128
AV&R (D?veloppement Interne)
Am?lioration de la strat?gie de palpage | 0 | 13 | 12 | 0 | 13 | 0 | 0 | 74 | [7 empty] | 112 | 0
5155
GEA Rutland
Support remote & onsite services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 11.25 | 4 | 3 | 2.5 | 0 | 0 | 0 | 21.25
5178
CHROMALLOY (Palm Beach)
One (1) Compressor Blade Profiling System R4 | 260 | 243 | 182 | 27 | 402 | 287 | 71 | 204 | 0.5 | 4.75 | 4.25 | 1.5 | 1 | 0 | 0 | 1676 | 12
5231
GEA Hooksett
Service part teaching | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
5264
BTL (Blades Technology Ltd)
Class F Inspection Software Modification and Inkjet Printer Retrofit | 0 | 30 | 0 | 354 | 46 | 8 | 205 | 94 | 5.5 | 10.5 | 9 | 4 | 2.5 | 0 | 0 | 737 | 31.5
5296
Lisi (Marmande)
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5305
Senior Aerospace (Thailand) Ltd.
One (1) LE and TE Robotic Profiling System | 244 | 229 | 260 | 18 | 453 | 358 | 629 | 211
5307
AECC Xian
HPC profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5327
GEA Bromont
Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5335
Lisi (Bologne)
Formation avanc?e et int?gration de 2 nouvelles r?f?rences | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5364
Techjet Airfoils Ltd
One (1) LE and TE Robotic Profiling System | 289 | 164 | 298 | 180 | 240 | 80 | 224 | 210
5371
BTL (Blades Technology Ltd)
05371 - Support Contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5374
GEA Bromont
Two (2) Profiling cells (One (1) L700 Pro & One (1) L703 Forge) R5 | 603 | 409 | 350 | 20 | 774 | 4 | 72 | 688 | 90.25 | 149.25 | 95.5 | 88 | 77.75 | 7 | 0
5380
TECT Power (Utica)
Profiling/Polishing Robotic Cell LE (Part 3423) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5387
CHROMALLOY (Palm Beach)
Garantie - One (1) Compressor Blade Profiling System R4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5388
Lisi (Marmande)
Garantie - One (1) GE9x Blades Robotic Profiling System R7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5429
Leistritz (Thailand) Ltd.
One (1) Leading and Trailing Edge Robotic Profiling Systems R5 | 314 | 165 | 257 | 8 | 337 | 740 | 126 | 188 | 333.5833 | 347.75 | 369.25 | 399.5833 | 328.5 | 54.5 | 0
5448
CHROMALLOY (Palm Beach)
DC01 - One (1) Compressor Blade Profiling System R4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5478
AV&R (D?veloppement Interne)
Fabrication de deux (2) Syst?mes Profilage Standards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5509
GEA Bromont
Two (2) LE Profiling 3rd Generation (CL Version) | 753 | 65 | 165 | 32 | 170 | 0 | 60 | 457 | 267.75 | 214.75 | 327.5 | 278 | 237.25 | 13 | 6.75
5515
GEA Bromont
Garantie: 2 Profiling cells L700 Pro & L703 Forge R5 | 603 | 409 | 350 | 20 | 774 | 4 | 72 | 688
5525
Safran Aero Boosters (Herstal)
Quatre (4) cellules de profilage LPC Leap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5528
Pratt & Whitney (PCI) - Columbus
Service - ?talonnage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 1.5 | 0 | 0
5535
AV&R (D?mos Client)
Tests de Profilage pour Leistritz | 2 | 0 | 13 | 0 | 33 | 64 | 0 | 0
5567
Hitchiner Manufacturing
Compressor Blade Profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5570
Lisi (Bologne)
RetroFit pour Profilage Classe F+ pour transfert RD3 GE9X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 97.25 | 96.75 | 81.25 | 67.5 | 16.5 | 28.75
5572
Propulsion Technologies International
Spare parts list | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5589
Hyatech
support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5608
GEA Bromont
Garantie de F-05509 - Two (2) LE Profiling 3rd Generation (CL Version) | 0 | 0 | 165 | 0 | 0 | 0 | 60 | 0
5619
GEA Hooksett
Updates on cell L-635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5654
Turbine Jet
Spare Parts UPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5667
Safran Aircraft Engines (Gennevilliers)
?tude - Profilage BA Leap R2 | 18 | 0 | 35 | 0 | 12 | 124 | 0 | 8 | 32.25 | 37 | 34.5 | 24.5 | 31.5 | 2 | 0
5679
CHROMALLOY (Newnan)
V-2500 Blade Develop New Recipes for New Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5691
Pratt & Whitney (PCI) - Columbus
profiling to deburring retrofit | 0 | 42 | 0 | 0 | 111 | 344 | 65 | 302 | 56 | 66.25 | 73 | 76.25 | 50.75 | 0 | 0
5709
GKN Aerospace (El Cajon)
Spare parts for F-05545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5710
GKN Aerospace (El Cajon)
Support for Malaysia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5713
BTL (Blades Technology Ltd)
Services - part prep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2.5 | 2 | 0 | 0 | 0
5719
Leistritz (Thailand) Ltd.
Garantie et support: One (1) Leading and Trailing Edge Robotic Profiling Systems R5 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 0
5752
Hyatech
(2) Compressor Blade Robotic Profiling Cells | 483 | 482 | 300 | 4 | 569 | 354 | 170 | 244
5755
AMRC - Advanced Manufacturing Research Center
One (1) COMBI Robotic Polishing and Profiling System + 1 year on site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5764
Lisi (Bologne)
formation avan??e et option | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.5 | 33 | 29 | 22 | 18.5 | 0 | 4.5
5801
BTL (Blades Technology Ltd)
05801 - Support contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5809
TECT Thomasville
Fan Blade Profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5825
GKN Aerospace (Manchester)
CF6-80C Fan Blade Profiling/Polishing | 559 | 237 | 602 | 0 | 464 | 1113 | 120 | 326
5831
Pratt & Whitney (PCI) - Columbus
Robot-reel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5834
Lisi (Bologne)
support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.75 | 2.5 | 1 | 5.25 | 0 | 0 | 0
5839
Superalloy Manufacturing Solutions Corporation
T-56 Military Compressor blade profiling/polishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5847
Pratt & Whitney East Hartford
One (1) Robotic Fan Blade LE/TE Profiling & Polishing System | 753 | 206 | 454 | 48 | 578 | 616 | 126 | 386
5848
Airfoil Services Sdn. Bhd. (ASSB)
Advanced training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 16.5 | 19.75 | 12.75 | 14.5167 | 43.9833 | 11
5851
Pratt & Whitney (PCI) - Columbus
Backup for Fanuc;s visit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5853
AV&R (D?mos Client)
D?mo Profilage Safran A?robooster | 3 | 0 | 18 | 0 | 15 | 60 | 0 | 8 | 1 | 7.75 | 2.75 | 1.5 | 7 | 0 | 0
5862
AVIC (Beijing) Manufacturing Technology Research Institute
ACAE;s CJ-1000 fan blade profiling | 493 | 171 | 478 | 8 | 267 | 920 | 208 | 198
5904
Lisi (Parthenay)
Une (1) cellule de profilage classe F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5906
Lisi (Parthenay)
Une (1) cellule de profilage grandes pi?ces | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5932
Safran Aero Boosters (Herstal)
Profilage de 1000 LPC Leap (MRL6) | 2 | 0 | 43 | 24 | 26 | 252 | 0 | 16
5938
CHROMALLOY (Palm Beach)
Study - Profiling Process Assessment for Clipped Forged Vanes R2 | 3 | 0 | 19 | 0 | 38 | 102 | 0 | 0
5940
Superalloy Manufacturing Solutions Corporation
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5949
Azad Engineering Pvt. Ltd
One (1) Robotic LE/TE Profiling System | 297 | 136 | 255 | 0 | 289 | 240 | 0 | 172
5959
Leistritz (Thailand) Ltd.
Banque de Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5966
Airfoil Services Sdn. Bhd. (ASSB)
support ? la carte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5983
Chromalloy (Tilburg)
One (1) Leading and Trailing Edge Robotic Profiling System | 315 | 135 | 177 | 8 | 262 | 268 | 214 | 148
5995
Airfoil Services Sdn. Bhd. (ASSB)
Advanced training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5996
GEA Rutland
Retrofit EZ profiling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5997
Propulsion Technologies International
Services - Signaux discrets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 DC2
GEA Bromont
Services - Impartition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE-Profiling
1940
Lufthansa Technik
One (1) Robotic Fan Blade Recontouring System | 963 | 155 | 280 | 0 | 346 | 312 | 63 | 290
1980
CHROMALLOY (Thailand)
Weld blending and profiling study | 6 | 31 | 119 | 0 | 38 | 533 | 0 | 45 | 59 | 60.3333 | 54 | 60.5 | 52.5 | 5.5 | 1
5022
Red River College
One (1) Leading & Trailing Edge Robotic RE-Profiling System R4 | 303 | 156 | 188 | 0 | 235 | 268 | 322 | 144 | 152.5 | 130 | 151.25 | 176.5 | 153.5 | 7 | 0
5067
Propulsion Technologies International
One (1) Robotic Fan Blade LE Repair System R9 (The First One) | 387 | 564 | 621 | 300 | 762 | 625 | 236 | 402 | 16.75 | 34.75 | 25 | 28.25 | 30.75 | 6.5 | 1
5200
Rolls-Royce Montreal
BR700 serie Fan blade reprofiling | 506 | 175 | 393 | 8 | 469 | 442 | 208 | 206
5385
Propulsion Technologies International
Garantie - One (1) Robotic Fan Blade LE Repair System R9 | 0 | 0 | 621 | 0 | 0 | 0 | 236 | 0
5418
Propulsion Technologies International
Amendement - One (1) Robotic Fan Blade LE Repair System R9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5446
Propulsion Technologies International
One (1) Robotic Fan Blade LE Repairing System R4 (The Second One) | 779 | 190 | 275 | 0 | 439 | 450 | 265 | 322 | 270.1667 | 318 | 330.5 | 297.5 | 312 | 7.5 | 0
5499
Safran Aircraft Engines (Saint Quentin)
Etude - Reprofilage BA Leap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5545
GKN Aerospace (El Cajon)
Three (3) Fan Blade robotic profiling & LE erosion removal systems R5 | 2309 | 298 | 1129 | 0 | 688 | 1236 | 282 | 484 | 870.4167 | 1005.7 | 932 | 919.3166 | 804.25 | 32 | 27
5603
Propulsion Technologies International
Ajout Mesure de corde cellule PTI R3 | 192 | 48 | 135 | 16 | 176 | 100 | 266 | 212 | 109.0833 | 105.75 | 141.75 | 125.25 | 139.5 | 0 | 26
5609
Red River College
Garantie F-05022 - One (1) Leading & Trailing Edge Robotic RE-Profiling System R4 | 0 | 0 | 188 | 0 | 0 | 0 | 322 | 0
5629
GKN Aerospace (Malaysia)
Two (2) Fan Blade robotic profiling & LE erosion removal systems | 1662 | 239 | 1061 | 0 | 413 | 628 | 1320 | 408 | 251.75 | 289.75 | 277.25 | 285.75 | 235 | 2.5 | 0
5645
Rolls-Royce Montreal
One (1) XWB Fan blade RE-Profiling Robotic System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5646
Rolls-Royce Montreal
XWB Fan blade ultrasonic skin measurement study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5655
Propulsion Technologies International
Amendement - One (1) Robotic Fan Blade LE Repair System R9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5673
Lufthansa Technik
Trent XWB Fan Blade Recontouring pre-engineering Phase | 138 | 43 | 100 | 0 | 157 | 250 | 0 | 154
5688
Propulsion Technologies International
services - CF34-8. CF34-10. CFM56-5A | 42 | 0 | 46 | 0 | 188 | 433 | 0 | 70
5704
CHROMALLOY (Palm Beach)
Services - Modifications for Thailand | 111 | 116 | 40 | 0 | 98 | 342 | 0 | 66
5718
GKN Aerospace (El Cajon)
Garantie et support : Three (3) Fan Blade robotic profiling & LE erosion removal systems R5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5725
SAESL
Fan blade reprofilling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5816
Lufthansa Technik
One (1) Trent XWB & Trent 1000 Fan Blade Recontouring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5817
AFI KLM E&M (Amsterdam)
Une (1) cellule de re-profiling de fan blade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5856
Propulsion Technologies International
5603 DC01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5910
GKN Aerospace (El Cajon)
Amendement - Three (3) Fan Blade robotic profiling & LE erosion removal systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5916
GEA CELMA
One (1) Fan Blade robotic profiling & LE erosion removal systems | 508 | 170 | 448 | 8 | 380 | 522 | 208 | 312
5926
Propulsion Technologies International
One (1) Robotic Fan Blade LE Repairing System (The Third One) - R2 | 819 | 163 | 192 | 8 | 250 | 192 | 128 | 186 | 9.75 | 15.5 | 21 | 25.5 | 17.5 | 0 | 0
5927
GKN Aerospace (Malaysia)
Amendement - DC-01 Two (2) Fan Blade robotic profiling & LE erosion removal systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5931
StandardAero
CF-34 Fan Blade Re-Profiling MRO for ;;Dallas Facility;; | 644 | 147 | 234 | 16 | 283 | 332 | 126 | 230
5936
Propulsion Technologies International
R?trofit Mat?riel & Fonctionnalit?s sur la 1?re Cellule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5956
Propulsion Technologies International
DC-02 One (1) Robotic Fan Blade LE Repairing System R4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5978
Airfoil Services Sdn. Bhd. (ASSB)
Mise ? jour BW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5994
CHROMALLOY (Thailand)
Weld blending and profiling study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surface Preparation Polishing
5530
Lisi (Marmande)
Service L-662 - mise ? jour syst?me de refroidissement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5614
Turbine Overhaul Services Pte Ltd (Pratt & Whitney)
One (1) Robotic HPT Blade Polishing System R2 | 315 | 132 | 137 | 0 | 177 | 160 | 63 | 172
5744
Turbine Overhaul Services Pte Ltd (Pratt & Whitney)
Robotic HPT Blade Polishing Study | 3 | 0 | 25 | 0 | 42 | 144 | 0 | 0
Thin Trailing Edge Profiling
4665
Safran Aircraft Engines (Gennevilliers)
?tude - Reprise Bord Fuite (Multiple LPT Profiling) Phase2 | 40 | 18 | 424 | 0 | 174 | 734 | 954 | 76
4743
Rolls-Royce Derby
One (1) Turbines Thin Trailing Edge profiling cell IPT R2 | 362 | 658 | 426 | 370 | 797 | 1098 | 0 | 623 | 130 | 134.5 | 143.75 | 182.75 | 126.25 | 25.5 | 24.5
4923
Rolls-Royce Derby
Thin Trailing Edge Feasibility Study on LPT | 0 | 0 | 40 | 0 | 20 | 160 | 0 | 0
4925
Rolls-Royce Derby
One (1) Turbines Thin Trailing Edge profiling cell IPT (ITP) | 0 | 100 | 200 | 200 | 150 | 600 | 0 | 150
5485
Rolls-Royce Derby
Thin Trailing Edge profiling cell on IPT Trent 900 (PCF) EP3+ | 0 | 100 | 200 | 200 | 150 | 600 | 0 | 150
5543
Rolls-Royce Derby
Ultra Fan Turbines Thin Trailing Edge profiling cell (PCF) test sur HT3 | 362 | 658 | 426 | 370 | 797 | 1098 | 0 | 623
5723
JV of AECC Xi;an and R&R
One (1) Turbines Thin Trailing Edge profiling cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5739
Rolls-Royce Derby
One (1) Turbines Thin Trailing Edge Profiling cell LPT (ABCF) | 0 | 100 | 200 | 200 | 150 | 600 | 0 | 150
5804
Rolls-Royce Derby
4743 DC02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5805
Rolls-Royce Derby
4743 DC01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tri-Blend
5153
BTL (Blades Technology Ltd)
Tri-Blend Process Capability Assessment | 0 | 0 | 40 | 0 | 7 | 324 | 0 | 0
5670
BTL (Blades Technology Ltd)
Tri-blend retrofit phase 1 study | 4 | 14 | 25 | 52 | 64 | 224 | 0 | 98 | 13 | 15.75 | 9.75 | 11.25 | 12.25 | 0 | 0
5873
Lisi (Bologne)
Option Tri-blend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5874
Lisi (Rzeszow)
Option Tri-blend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5877
AV&R (D?veloppement Interne)
D?veloppement triblend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 28.75 | 30.25 | 33.25 | 40.5 | 0 | 0.5
5905
Lisi (Parthenay)
?tude VSV tri-blend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5909
Safran Aero Boosters (Herstal)
D?veloppement option tri-blend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5950
Pietro Rosa T.B.M
D?veloppement Tri-Blend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ultra-Polishing
4799
GEA Bromont
2 x UltraPolish Repeat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5302
GEA Bromont
Amendement - UltraPolish cell | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weld & A.M. Blending
1911
Delta TechOps
Delta Onsite Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1987
Delta TechOps
Delta Onsite Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4491
Airfoils Advanced Solutions
?tude de tip blending HPC GE90 | 0 | 0 | 3 | 0 | 0 | 80 | 0 | 0
4529
Delta TechOps
New tip recipe + weld adjustment + training | 0 | 0 | 24 | 52 | 0 | 334 | 0 | 27
4839
AV&R (D?veloppement Interne)
Blending M14 PH1 Belt sander priorit? 1 (0.095) | 0 | 77 | 157 | 173 | 341 | 74 | 0 | 48
4845
AV&R (D?veloppement Interne)
Blending M22- PH 0 ? partir de cordon de soudure rough HARDTOOL (1.02) | 0 | 0 | 20 | 0 | 45 | 45 | 0 | 0
4846
AV&R (D?veloppement Interne)
Blending M28 Revoir l;algo de filtrage pour l;adaptive en Ry (axe qui sort du edge) (1.05) | 0 | 0 | 39 | 134 | 0 | 45 | 0 | 0
5006
GEA CAR
Amendement - Tip Blending (ATI Singapore) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5410
GEA Bromont
Service code modifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5426
CHROMALLOY (Thailand)
One (1) HPC Weld Blending & Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5464
Propulsion Technologies International
Partenariat D?veloppement R?paration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5467
GEA Bromont
Service code modifications amendement DC01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5502
Safran Aircraft Engines Mexico (Quer?taro)
Etude - Blending joint de colle BA Leap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5579
CHROMALLOY (Thailand)
HPC AM polishing & Profiling Study | 5 | 0 | 50 | 0 | 23 | 348 | 0 | 0
5580
CHROMALLOY (Thailand)
One (1) COMBI Robotic Polishing and Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5606
Airfoil Services Sdn. Bhd. (ASSB)
HPC Weld Blend & Profiling Study | 6 | 31 | 119 | 0 | 38 | 533 | 0 | 45
5607
Airfoil Services Sdn. Bhd. (ASSB)
One (1) HPC Weld Blending & Profiling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5665
AV&R (D?veloppement Interne)
D?veloppement pin blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.4167 | 468.6666 | 468.4999 | 474.2498 | 390 | 9.5 | 5.5
5698
CHROMALLOY (Thailand)
HPC Tip Weld blending Study | 6 | 31 | 119 | 0 | 38 | 533 | 0 | 45
5726
Turbine Overhaul Services Pte Ltd (Pratt & Whitney)
HPC Weld Blend & Profiling cell | 424 | 206 | 299 | 0 | 250 | 1018 | 100 | 228
5727
Turbine Overhaul Services Pte Ltd (Pratt & Whitney)
HPC Weld blending Study | 17 | 0 | 64 | 0 | 111 | 340 | 0 | 8
5732
Rolls-Royce Derby
Blisk blending and reprofiling system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5734
Rolls-Royce Derby
Fan blade blending and reprofiling study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5784
Rolls-Royce Derby
Blisk blending and reprofiling study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5878
AV&R (D?veloppement Interne)
D?veloppement tip blending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5880
AV&R (D?mos Client)
GKN Patch Weld Blend Trials | 3 | 0 | 5 | 0 | 10 | 24 | 0 | 0 | 9.5 | 1 | 7.5 | 6.75 | 7.5 | 0 | 0
DC1
Delta TechOps
Spare parts Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
List2015
Delta TechOps
Spare parts Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxx
Airfoil Services Sdn. Bhd. (ASSB)
Tip Blending System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 39079 | 24900 | 39959 | 19384 | 47409 | 83971 | 16224 | 34321 | 6445.8 | 6982.1499 | 7019.1332 | 7132.9997 | 6327.3333 | 336.7333 | 235.75

## Pivot Graph
Column Labels
| Sum of monday | [10 empty] | Sum of tuesday | [10 empty] | Sum of wednesday | [10 empty] | Sum of thursday | [10 empty] | Sum of friday | [10 empty] | Sum of saturday | [10 empty] | Sum of sunday | [10 empty] | Total Sum of monday | Total Sum of tuesday | Total Sum of wednesday | Total Sum of thursday | Total Sum of friday | Total Sum of saturday | Total Sum of sunday
Row Labels | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending | AVI - Blade | Controlled Polishing | Cosmetic Polishing | Deburring | Pin Blending | Polishing Non-Attribu? | Profiling | RE-Profiling | Thin Trailing Edge Profiling | Tri-Blend | Weld & A.M. Blending
Babineau; Simon |  | 31 | 1.25 |  | 117.3333 | 72.25 |  |  |  | 1.5 | 17.25 |  | 27.5 | 0 |  | 103.75 | 77 |  |  |  | 16.25 | 24.25 |  | 17.25 | 0 |  | 103.5 | 79.5 |  |  |  | 6 | 37.5 |  | 33 | 0 |  | 122.4167 | 76.5 |  |  |  | 8 | 37 |  | 28.75 | 0 |  | 101.5 | 72.75 |  |  |  | 21.75 | 12.25 |  | 14.25 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 8 | 0 |  | 0 | 0 |  |  |  | 0 | 0 | 240.5833 | 248.75 | 243.75 | 276.9167 | 237 | 14.25 | 8
Bonvouloir; Alexandre |  | 24 | 0.5 |  | 8 | 43.5 | 33 | 39 | 64 |  |  |  | 36 | 2 |  | 8 | 59 | 52 | 45.5 | 54 |  |  |  | 31 | 3 |  | 14 | 52 | 57.5 | 43 | 53.5 |  |  |  | 43.5 | 5 |  | 24.5 | 52.5 | 48 | 38.5 | 71.5 |  |  |  | 30.5 | 1 |  | 7 | 35.5 | 48.5 | 48 | 51.5 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 11.5 | 13.5 |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 13.5 |  |  | 212 | 256.5 | 254 | 283.5 | 222 | 25 | 13.5
Caron-Rollin; Samuel |  |  |  |  | 30 | [5 empty] | 16 |  |  |  |  | 30 | [5 empty] | 16 |  |  |  |  | 30 | [5 empty] | 19 |  |  |  |  | 30 | [5 empty] | 30.5 |  |  |  |  | 20.5 | [5 empty] | 18.5 |  |  |  |  | 5 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 46 | 46 | 49 | 60.5 | 39 | 5 | 0
D;amours; Guillaume |  | 9 | 2.75 |  | 14.25 | 5.75 | 1.5 | 5.25 | 11.25 | 6 | 10.8334 |  | 17.75 | 12.75 |  | 13.1666 | 8.25 | 3.75 | 10.3333 | 13.75 | 7 | 6.3333 |  | 13.8333 | 10.5833 |  | 19.0833 | 3.25 | 5.5 | 18 | 14.25 | 6 | 5.75 |  | 19.6666 | 9.25 |  | 15.4166 | 5.75 | 4.0833 | 21.5833 | 18.25 | 6 | 11.3332 |  | 11.75 | 5.75 |  | 11.0834 | 16.25 | 1 | 7.75 | 12.25 | 5 | 8.8334 |  | 1.5 | 0 |  | 0 | 0 | 0 | 1 | 11.5 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 1 | 11 | 0 | 0 | 66.5834 | 93.0832 | 96.2499 | 111.333 | 79.6668 | 14 | 12
Dupuis; Vincent | 52.25 | [10 empty] | 49.5 | [10 empty] | 48.5 | [10 empty] | 77.5 | [10 empty] | 47.5 | [10 empty] | 0 | [10 empty] | 0 | [10 empty] | 52.25 | 49.5 | 48.5 | 77.5 | 47.5 | 0 | 0
Falardeau; Louis-Xavier |  | 12 | 5.5 | 7 | 9.5 | 55.5 | 44.25 | 1.5 | 1 |  | 51.25 |  | 5.5 | 2 | 5.5 | 11.75 | 67.5 | 38.75 | 11.5 | 1 |  | 58.75 |  | 8.0833 | 3 | 4.5 | 11 | 67.8 | 36.1667 | 9.25 | 2 |  | 52 |  | 8.25 | 1.5 | 1.5 | 13 | 55.75 | 33.75 | 5.5 | 1.5 |  | 38.5 |  | 2 | 3.5 | 2.25 | 14.75 | 63.25 | 50.5 | 8 | 0 |  | 31.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 187.5 | 202.25 | 193.8 | 159.25 | 176 | 0 | 1
Laarich; Walid |  | 138 | 33 |  |  | 7.5 | 7.5 | 80.5 |  |  | 8 |  | 130 | 31 |  |  | 17 | 16 | 94 |  |  | 8 |  | 122.5 | 33 |  |  | 7.5 | 14.5 | 98.5 |  |  | 7.8333 |  | 139.5 | 34 |  |  | 7.5 | 12.5 | 93.5 |  |  | 6 |  | 112.5 | 26 |  |  | 11 | 12 | 110 |  |  | 0 |  | 0 | 10.5 |  |  | 0 | 0 | 11 |  |  | 0 |  | 5 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 274.5 | 296 | 283.8333 | 293 | 271.5 | 21.5 | 5
Landry; Christian |  | 80 | 0 |  |  | 3 | 106 | 0 | 5.5 |  |  |  | 86.5 | 0 |  |  | 5.5 | 115.75 | 0 | 4 |  |  |  | 94 | 2 |  |  | 0 | 127.5 | 0 | 9 |  |  |  | 84 | 0 |  |  | 0 | 98.75 | 4 | 5 |  |  |  | 94.5 | 0 |  |  | 0 | 79.2667 | 0.5 | 4 |  |  |  | 0 | 0 |  |  | 0 | 66.4833 | 0 | 0 |  |  |  | 15 | 0 |  |  | 0 | 25 | 0 | 0 |  |  | 194.5 | 211.75 | 232.5 | 191.75 | 178.2667 | 66.4833 | 40
Lecours; Mathieu |  | 7.5 | 0 |  | 102.5 | 40.5 | 0 |  | 0 | 2 | 81 |  | 9 | 0 |  | 95 | 46 | 0 |  | 0 | 0 | 79.5 |  | 7.5 | 0 |  | 112 | 41.5 | 0.5 |  | 1 | 1.5 | 100 |  | 2 | 0 |  | 143 | 49.75 | 0 |  | 0 | 0 | 98.5 |  | 5 | 0.5 |  | 87.5 | 58 | 0 |  | 0 | 0 | 89 |  | 0 | 0 |  | 2 | 0 | 0 |  | 0 | 0 | 9.5 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 4 | 233.5 | 229.5 | 264 | 293.25 | 240 | 11.5 | 4
Marcotte; Maxime |  | 58.5 |  |  | 27 | 9.5 | 103.3333 | 24 | 4 |  |  |  | 63 |  |  | 39 | 5.5 | 115 | 34 | 10 |  |  |  | 56 |  |  | 30.4167 | 17 | 110.75 | 51 | 9.5 |  |  |  | 56.5 |  |  | 40.5 | 24.5 | 118.25 | 58 | 11.5 |  |  |  | 65.8333 |  |  | 39.25 | 20 | 87.5 | 40 | 4 |  |  |  | 25.5 |  |  | 0 | 0 | 18 | 0 | 0 |  |  |  | 20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 226.3333 | 266.5 | 274.6667 | 309.25 | 256.5833 | 43.5 | 20
Ouimet-Daigneault; Vincent |  |  |  |  | 22.25 | 14 | 5.5 |  |  | 4 | 7.5 |  |  |  |  | 33.75 | 8.5 | 7.25 |  |  | 4.5 | 9.5 |  |  |  |  | 28.5 | 2.5 | 0 |  |  | 0 | 7.75 |  |  |  |  | 24.5 | 2.5 | 0 |  |  | 0 | 11.5 |  |  |  |  | 12.5 | 1 | 0 |  |  | 0 | 13 |  |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 53.25 | 63.5 | 38.75 | 38.5 | 26.5 | 0 | 0
Stoycheff; Normand |  | 0 |  |  |  |  | 10.5 | 1 | 0 |  |  |  | 0.5 |  |  |  |  | 22.75 | 0.5 | 0.5 |  |  |  | 0.5 |  |  |  |  | 11.5 | 1.5 | 0 |  |  |  | 0.5 |  |  |  |  | 12 | 2.5 | 1 |  |  |  | 0 |  |  |  |  | 10.5 | 3.5 | 0.5 |  |  |  | 0 |  |  |  |  | 6 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 11.5 | 24.25 | 13.5 | 16 | 14.5 | 6 | 0
Grand Total | 52.25 | 360 | 43 | 7 | 330.8333 | 251.5 | 311.5833 | 151.25 | 85.75 | 13.5 | 191.8334 | 49.5 | 375.75 | 47.75 | 5.5 | 334.4166 | 294.25 | 371.25 | 195.8333 | 83.25 | 27.75 | 202.3333 | 48.5 | 350.6666 | 51.5833 | 4.5 | 348.5 | 271.05 | 363.9167 | 221.25 | 89.25 | 13.5 | 229.8333 | 77.5 | 386.9166 | 49.75 | 1.5 | 413.3333 | 274.75 | 327.3333 | 223.5833 | 108.75 | 14 | 233.3332 | 47.5 | 350.8333 | 36.75 | 2.25 | 294.0834 | 277.75 | 289.2667 | 217.75 | 72.25 | 26.75 | 173.3334 | 0 | 41.25 | 10.5 | 0 | 7 | 0 | 90.4833 | 23.5 | 25 | 0 | 9.5 | 0 | 48 | 0 | 1 | 0 | 0 | 25 | 1 | 24.5 | 0 | 4 | 1798.5 | 1987.5832 | 1992.5499 | 2110.7497 | 1788.5168 | 207.2333 | 103.5

## Project Charting
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Week definition
Row Labels
201843
1
2018-43 (01/10 - 06/10)
201844
2
2018-44 (07/10 - 13/10)
201845
3
2018-45 (14/10 - 20/10)
201846
4
2018-46 (21/10 - 27/10)
201847
5
2018-47 (28/10 - 31/10)
201848
6
2018-48 (01/11 - 03/11)
201849
7
2018-49 (04/11 - 10/11)
201850
8
2018-50 (11/11 - 17/11)
201851
9
2018-51 (18/11 - 24/11)
201852
10
2018-52 (25/11 - 30/11)
201853
11
2018-53 (01/12 - 01/12)
201854
12
2018-54 (02/12 - 08/12)
201855
13
2018-55 (09/12 - 15/12)
201856
14
2018-56 (16/12 - 22/12)
201857
15
2018-57 (23/12 - 29/12)
201858
16
2018-58 (30/12 - 31/12)
201901
17
2019-01 (01/01 - 05/01)
201902
18
2019-02 (06/01 - 12/01)
201903
19
2019-03 (13/01 - 19/01)
201904
20
2019-04 (20/01 - 26/01)
201905
21
2019-05 (27/01 - 31/01)
201906
22
2019-06 (01/02 - 02/02)
201907
23
2019-07 (03/02 - 09/02)
201908
24
2019-08 (10/02 - 16/02)
201909
25
2019-09 (17/02 - 23/02)
201910
26
2019-10 (24/02 - 28/02)
201911
27
2019-11 (01/03 - 02/03)
201912
28
2019-12 (03/03 - 09/03)
201913
29
2019-13 (10/03 - 16/03)
201914
30
2019-14 (17/03 - 23/03)
201915
31
2019-15 (24/03 - 30/03)
201916
32
2019-16 (31/03 - 31/03)
201917
33
2019-17 (01/04 - 06/04)
201918
34
2019-18 (07/04 - 13/04)
201919
35
2019-19 (14/04 - 20/04)
201920
1009
2019-20 (21/04 - 27/04)
201921
2009
2019-21 (28/04 - 30/04)
201922
2010
2019-22 (01/05 - 04/05)
201923
2011
2019-23 (05/05 - 11/05)
201924
3010
2019-24 (12/05 - 18/05)
201925
3011
2019-25 (19/05 - 25/05)
201926
4011
2019-26 (26/05 - 31/05)
201927
4013
2019-27 (01/06 - 01/06)
201928
4012
2019-28 (02/06 - 08/06)
201929
4014
2019-29 (09/06 - 15/06)
201930
5011
2019-30 (16/06 - 22/06)
201931
5012
2019-31 (23/06 - 29/06)
201932
5014
2019-32 (30/06 - 30/06)
201933
5013
2019-33 (01/07 - 06/07)
201934
5015
2019-34 (07/07 - 13/07)
201935
5016
2019-35 (14/07 - 20/07)
201936
5017
2019-36 (21/07 - 27/07)
201937
5018
2019-37 (28/07 - 31/07)
201938
5019
2019-38 (01/08 - 03/08)
201939
5020
2019-39 (04/08 - 10/08)
Grand Total

## Process stats
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## ResourceOnProject
Row Labels | Sum of totalHours
AV&R (D?mos Client)
Tests de Polissage & Profilage pour N.E.A.P.
Atelier
Richer; Frederic
Atelier | 40
FR
Bonvouloir; Alexandre
Orange Mechanique | 62
D;amours; Guillaume
Supervisor | 34.25
Duval Gagn?; S?bastien
Blackbird | 135
PM
St-Amand; Eric
Orange Mechanique | 37.5
Grand Total | 308.75
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.